## Sheet1
WO | Description | Status | Total Allocation in MD | Remaining Allocation in MD | % Done | Required MD to finish | Exact hour Spent | PSA Dependancy | Comment | Assignee
CAP-8607 | Indus activities CESARE | In Progress | 33 | 11 | [5 empty] | Gopinath/pranab
CAP-17268 | Windows migration licence Gopi | Pending | 60 | 0 | [5 empty] | Gopinath
CAP-17584 | Migration Licence lot 2 Technical India B2 | In Progress | 105 | 3 | [5 empty] | Gopinath
CAP-18254 | HPC Solver License B2 | To Do | 23 | 18.5 | [5 empty] | Gopinath/Manish/Jerome
CAP-17619 | W2016 Artisan Studio B2 | To Do | 10 | 10 | [5 empty] | Gopi
CAP-17064 | Saturne GestLic Gopinath | In Progress | 42 | 6 | [5 empty] | Gopi
CAP-18289 | DSPACE B1 | To Do | 13 | 10 | [5 empty] | Gopi
CAP-19041 | Gest Gopi | In Progress | 21 | 8 | [5 empty] | Gopi
CAP-18027 | Digital Boost integration activities Gopi | In Progress | 12 | 6 | 90 | 2 | 40 |  |  | Gopi
CAP-19639 | E-Motors license server Gopi | To Do | 15 | 12 | [5 empty] | Gopi
CAP-13415 | Indian activities Indus RDMS-E | In Progress | 40 | 7 | 75 | 7 | 204 | No | As we have working on blocking Incident | Pranab
CAP-15544 | UNM3D ATRIUMv2 | In Progress | 55.25 | 20.5 | 60 | 20 | 160 | Yes | After doing CustoPSA we have to verify each invidiual functional gamme scripts with PSA | Pranab/Arun
CAP-18002 | UNEMB Windows 2016 migration (part 2) Pranab | To Do | 28 | 15 | 65 | 15 | 0 | Yes | We have to update automate -DLL from Lascome to complete blocking issue during testing cycle | Pranab/Manish
CAP-17580 | W2016 OASSIS/PLM | In Progress | 28.6 | 6 | 80 | 6 | 0 | Yes | PSA validation post Tomcate installation and URL Migration | Pranab
CAP-18590 | PLM SW DOTI Pranab | Pending | 30 | 9 | 85 | 5 | 0 | No | GOAP,XAPP,FICA Documentation purpose | Pranab
CAP-19589 | ADvitium Migration | In Progress | 41 | 4.75 | 90 | 4 | 0 | Yes | Deploy patch during blocking issue in testing cycle | Pranab/Arun
CAP-15586 | Unemb integration 2020 Indus RD activities BO | To Do | 4 | 3 | 90 | 3 | 0 | No | GOAP,XAPP,FICA Documentation purpose | Pranab
CAP-16804 | Reactivity HNCT Flux Aruna | Pending | 48 | 0 | [5 empty] | Arun
CAP-17335 | Upgrade DOORS version Indus Activities | In Progress | 16 | 0 | [5 empty] | Arun
CAP-17664 | Capital new version Technical Technical Ind | In Progress | 48 | 21 | [5 empty] | Arun
CAP-16396 | Airflow and planisware Updates Aruna | Pending | 43 | 35 | [5 empty] | Arun
CAP-18289 | ATTM | In Progress | 16 | 7 | [5 empty] | Arun/Manish
CAP-14152 | INDUS-CESARE - PPR Flux ONL + Error process | Pending | 9 | 0 | [5 empty] | Arun
CAP-18005 | CervantesV2 Servers Migration | Pending | 48 | 17 | [5 empty] | Arun
CAP-18407 | Gaele Synergy B1 | To Do | 55 | 30.75 | [5 empty] | Manish
CAP-18285 | MEPLM New plateform Manish | Pending | 55.5 | 1.25 | [5 empty] | Smruti/Manish
CAP-17385 | MEPLM Indus Maintenance | To Do | 18 | 15 | [5 empty] | Smruti